## Teorie
Test Plan / Test Set / Test Cases
Test Plan
Un document care descrie scopul, obiectivele, resursele și programul activităților de testare prevăzute.
Identifică printre altele
▪ Ce urmează a fi testat
▪ Sarcinile de testare, cine va îndeplini fiecare sarcină
▪ Gradul de independență al testerului
▪ Mediul de testare
▪ Riscuri ▪ Când se termină testarea? Ex 95% din testele critice trebuie sa fie PASS
Test Case : Succesiune de pași =>funcționalitatea produsului
Test Set: colecție de Test Case-uri care se referă la acceeasi funcționalitate ( grupate împreună)
Ce conține un Test Case?
Test Set Id
Test Set Name
Test Case Id
Test Priority
Test Case Name
Description / Summary
Test Step
Test Data
Expected Results
Actual Result
Status(Fail/Pass)
Notes Requirements
Pre-conditions
Post-conditions

## TEST CASE+BUGS
AUT (Application Under Test): https://demo.guru99.com/payment-gateway/purchasetoy.php
Test Set # (Test Scenarion) | Test Case # | Test Set (Test Scenarion) | Test Case | Pre-condintions | Post_conditions | Test Priority | Description/Summary | Test Steps | Test Data | Expected Result | Actual Result | Status Pass/Fail
G1 | TCG1 | Generate Card Number | Generate Card Number | chrome, firefox , edge available | - | 1 | We want to generate a valid card number | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. go to Generate Card Number | - | we should get a valid card Number with CVV, expiration date, Credit Limit | we receive a valid card number | PASS
C1 | TC1 | Cart | we can make an order with valid card number | 1. chrome, firefox , edge available 2. we get a valid CardNumber from TCG1 | Able to complite an order | 1 | we should be able to complite an order | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card 5. Press Buy | a valid cardNumber | we should receive Payment succesfuul and an Order ID | receive Payment succesfuul and an Order ID | PASS
C1 | TC2 | Cart | we should not make an order with invalid cardNumber | chrome, firefox , edge available | Able to complite an order With invalid CardNumber | 1 | we should be able to complite an order | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (invalid card) 5. Press Buy | invalid card | we should receive an error message | receive Payment succesfuul and an Order ID | FAILED
C1 | TC3 | Cart | CardNumber with Characters | 1.Chrome,Firefox, Edge Available | Able to complite an order | 1 | we should not be able to complite an order with Card Number with Characters | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (invalid card Characters) 5. Press Buy | invalid card Characters CVV:- 201 Exp:- 09/2025 | we should not make an order | receive Payment succesfuul and an Order ID 989105 | FAILED
C1 | TC4 | Cart | CardNumber is empty | 1.Chrome,Firefox, Edge Available | Receive an pop-up with: Check card number is 16 digits. | 1 | 1.We Should Not Be Able To Complite An Order 2. Receive an pop-up with: Check card number is 16 digits. | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. Blank Card (No Information) 5. Press Buy | Blank Card | We Receive An Pop-up With: Check Card Number Is 16 Digits.! | Receive Pop-Up :Check card number is 16 digits! | PASS
C1 | TC5 | Cart | CardNumber digit<16 (ex: 12) | 1.Chrome,Firefox, Edge Available | Receive an pop-up with: Check card number is 16 digits. | 1 | 1.We Should Not Be Able To Complite An Order 2. Receive an pop-up with: Check card number is 16 digits. | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. Fill the information for the card 5. Card Number digit = (12) 1 ..12 6.Press Buy | Invalid Card | We Receive An Pop-up With: Check Card Number Is 16 Digits.! | Receive Pop-Up :Check card number is 16 digits! | PASS
C1 | TC6 | Cart | Month in the past | 1.Chrome,Firefox, Edge Available | we Receive: Payment successfull! And an Order ID 867857 | 1 | 1. We should Not be able to complite an order with Month of the Card in the past | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (valid card) 5. month will be in the past 6.Press buy | Valid Card : Card Number : 4801695876515651 Expiration Month 05 Expiration Year 2018 CVV Code: 287 | Should Not have an Order With month of the card in the past | Payment successfull! And an Order ID 867857 | FAILED
C1 | TC7 | Cart | Expiration Year in the past | 1.Chrome,Firefox, Edge Available | we Receive: Payment successfull! And an Order ID 590460 | 1 | 1. We should Not be able to complite an order with Year of the Card in the past | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (valid card) 5. Year will be in the past 6.Press buy | Card Number 4801695876515651 Expiration Month 01 Expiration Year 2017 CVV Code 287 | Should Not have an Order With Year of the card in the past | Payment successfull! And an Order ID 590460 | FAILED
C1 | TC8 | Cart | CVV Code with charcters | 1.Chrome,Firefox, Edge Available | we Receive: Payment successfull! And an Order ID 962184 | 1 | we should not be able to complite an order with INVALID CVV | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (valid card) 5. CVV CODE will be with characters 6.Press buy | Card Number 4801695876515651 Expiration Month 01 Expiration Year 2018 CVV Code nfh | Should Not have an Order With INVALID CVV | Payment successfull! And an Order ID 962184 | FAILED
C1 | TC9 | Cart | try to make a transaction with Pay Ammount > Credit Limit | 1.Chrome,Firefox, Edge Available | we Receive: Payment successfull! And an Order ID 136708 | 1 | test if i am able to do an order with the valid card but PAY AMMOUNT > CREDIT CARD LIMIT. | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (valid card) 5. Press Buy. | Card Number 480169587651565 Expiration Month 01 Expiration Year 2018 CVV Code 287 | Should not be able to do an order | Payment successfull! And an Order ID 136708 | FAILED
C1 | TC10 | Check Credit Card Limit | Verify Limit card after a transaction | 1. chrome, firefox , edge available 2. we get a valid CardNumber from TCG1 | we Receive: Payment successfull! And an Order ID 718265 | 1 | we should see the limit of the card | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 9 3. press Buy 4. fill all information for card (invalid card) 5. Press Buy | valid card Card Number 290139586653523 Expiration Month 02 Expiration Year 2018 CVV Code 253 | we should get an error message | receive Payment succesfuul and an Order ID 718265 | FAILED
BugId | Description | TestCaseId | Status | Raised By | Application Version | Steps to Reproduce | Expected Results | Actual Result | Priority | Severity | Files attached | Assigned to
B1 | we should not make an order with invalid cardNumber | TC2 | OPEN | Ratiu Catalin M. | - | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (invalid card) 5. Press Buy | We should receive an error message | Receive Payment successfull! and an Order ID | HIGH | MODERATE
B2 | We should not make an order with invalid month at the Card | TC6 | OPEN | Ratiu Catalin M. | - | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (valid card) 5. month will be in the past 6.Press buy | We should receive an error message | Payment successfull! And an Order ID 867857 | HIGH | MODERATE
B3 | We should not make an order with invalid year at the Card | TC7 | OPEN | Ratiu Catalin M. | - | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (valid card) 5. Year will be in the past 6.Press buy | We should receive an error message | Payment successfull! And an Order ID 962184 | HIGH | MODERATE
B4 | We should not make an order with invalid CVV at the Card | TC8 | OPEN | Ratiu Catalin M. | - | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (valid card) 5. CVV CODE will be with characters 6.Press buy | We should receive an error message | Payment successfull! And an Order ID 962184 | HIGH | MODERATE
B5 | I am able to do an order with the valid card but PAY AMMOUNT > CREDIT CARD LIMIT. | TC9 | OPEN | Ratiu Catalin M. | - | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (valid card) 5. Press Buy. | Should not be able to do an order | Payment successfull! And an Order ID 136708 | HIGH | MINOR
B6 | we should see the limit of the card | TC10 | OPEN | Ratiu Catalin M. | - | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 9 3. press Buy 4. fill all information for card (invalid card) 5. Press Buy | We should see the limit of the card | Receive Payment succesfuul and an Order ID 718265 | HIGH | TRIVIAL
B7 | We should not be able to do an order with invalid characters at the Card | TC3 | OPEN | Ratiu Catalin M. | - | 1. Open https://demo.guru99.com/payment-gateway/purchasetoy.php 2. choose: Quantity 1 3. press Buy 4. fill all information for card (invalid card Characters) 5. Press Buy | We should not be able to do an order with invalid characters at the Card | Receive Payment succesfuul and an Order ID 989105 | HIGH | MAJOR